## Control Matrix
Control ID | Phase | Control Area | Checklist Item | Service / Component | Primary Owner Team | Source Documents / Sections | Mapped Services
AZ-001 | Phase 0 | Architecture / Scope | Define POC site, environment, and criticality boundary | Program / Platform | Platform | AIO Governance; ADLS | AIO Governance; ADLS
AZ-002 | Phase 0 | Architecture / Scope | Decide connected vs semi-disconnected operating model | Connectivity / Resilience | Platform | AIO Governance; Key Vault; PostgreSQL; MySQL | AIO Governance; Key Vault; PostgreSQL; MySQL
AZ-003 | Phase 0 | Architecture / Scope | Select primary cloud eventing pattern (Event Hubs and/or Event Grid) | Integration / Messaging | App | Event Hubs; Event Grid | Event Hubs; Event Grid
AZ-004 | Phase 0 | Architecture / Scope | Select retained storage pattern (ADLS) and analytics scope (Databricks optional) | Storage / Analytics | App | ADLS; Databricks | ADLS; Databricks
AZ-005 | Phase 0 | Architecture / Scope | Choose one edge database path (PostgreSQL or MySQL) for the POC | Database | App | PostgreSQL; MySQL | PostgreSQL; MySQL
GOV-001 | Phase 1 | Landing Zone / Governance | Create dedicated subscription and/or resource group aligned to site boundary | Azure Landing Zone | Platform | AIO Governance; ADLS; Azure Monitor; Event Hubs | AIO Governance; ADLS; Azure Monitor; Event Hubs
GOV-002 | Phase 1 | Landing Zone / Governance | Use one AIO instance per resource group | AIO / Azure | Platform | AIO Governance | AIO Governance
GOV-003 | Phase 1 | Landing Zone / Governance | Apply required tags: site, environment, owner, criticality, cost center, connectivity model, data classification, patch ring | Azure Resource Manager | Platform | AIO Governance; ADLS; Azure Monitor; Event Hubs; Event Grid | AIO Governance; ADLS; Azure Monitor; Event Hubs; Event Grid
GOV-004 | Phase 1 | Landing Zone / Governance | Document ownership across platform, OT, security, app/integration, data/analytics, PKI, and operations | Operating Model | Platform | Event Grid; Event Hubs; Key Vault; Databricks; Azure Monitor | Event Grid; Event Hubs; Key Vault; Databricks; Azure Monitor
IAM-001 | Phase 1 | Identity / Access | Use group-based Azure RBAC instead of direct user assignments | Entra ID / Azure RBAC | Security | AIO Governance; Key Vault; Azure Monitor | AIO Governance; Key Vault; Azure Monitor
IAM-002 | Phase 1 | Identity / Access | Separate human access roles for platform admin, security operator, observability reader, OT operator, and app deployer | Entra ID / Azure RBAC | Security | AIO Governance; Azure Monitor; Event Hubs; Event Grid | AIO Governance; Azure Monitor; Event Hubs; Event Grid
IAM-003 | Phase 1 | Identity / Access | Protect privileged access with MFA, Conditional Access, and PIM where available | Entra ID | Security | AIO Governance; Key Vault; Azure Monitor | AIO Governance; Key Vault; Azure Monitor
K3S-001 | Phase 2 | Cluster Baseline | Build Arc-enabled K3s cluster on hardened supported host baseline | K3s / Arc | Platform | AIO Governance; ADLS; Event Hubs | AIO Governance; ADLS; Event Hubs
K3S-002 | Phase 2 | Cluster Baseline | Enable K3s secrets encryption at rest | K3s | Platform | Key Vault; PostgreSQL; MySQL | Key Vault; PostgreSQL; MySQL
K3S-003 | Phase 2 | Cluster Baseline | Enable protect-kernel-defaults / CIS-aligned host controls | K3s / Host OS | Platform | Key Vault; PostgreSQL; MySQL; AIO Governance | Key Vault; PostgreSQL; MySQL; AIO Governance
K3S-004 | Phase 2 | Cluster Baseline | Enable API server audit logging and controlled SSH break-glass | K3s / Host OS | Platform | Key Vault; AIO Governance; PostgreSQL; MySQL | Key Vault; AIO Governance; PostgreSQL; MySQL
ARC-001 | Phase 2 | Arc Features | Arc-enable the K3s cluster | Azure Arc | Platform | AIO Governance; Azure Monitor; Event Hubs; ADLS | AIO Governance; Azure Monitor; Event Hubs; ADLS
ARC-002 | Phase 2 | Arc Features | Enable OIDC issuer, workload identity, cluster connect, and custom locations | Azure Arc | Platform | AIO Governance; PostgreSQL; MySQL | AIO Governance; PostgreSQL; MySQL
ARC-003 | Phase 2 | Arc Features | Create baseline namespaces for arc, aio, platform-security, line-apps, and optional database namespaces | Kubernetes | Platform | AIO Governance; PostgreSQL; MySQL | AIO Governance; PostgreSQL; MySQL
ARC-004 | Phase 2 | Arc Features | Use custom locations only for namespaces that require Azure-side deployment targets | Azure Arc / Kubernetes | Platform | AIO Governance; PostgreSQL; MySQL | AIO Governance; PostgreSQL; MySQL
PKI-001 | Phase 3 | Certificates / PKI | Adopt enterprise or plant-controlled CA / issuer for production-style AIO and DB trust | PKI / Certificates | Security | Certificate Management; AIO Governance; PostgreSQL; MySQL | Certificate Management; AIO Governance; PostgreSQL; MySQL
PKI-002 | Phase 3 | Certificates / PKI | Define certificate sets for AIO, workload TLS, client CA bundles, admin/backup certs as needed | PKI / Certificates | Security | Certificate Management; PostgreSQL; MySQL | Certificate Management; PostgreSQL; MySQL
IAM-004 | Phase 3 | Workload Identity | Create dedicated user-assigned managed identities per trust boundary | Entra ID / Managed Identity | Security | AIO Governance; Key Vault; PostgreSQL; MySQL | AIO Governance; Key Vault; PostgreSQL; MySQL
IAM-005 | Phase 3 | Workload Identity | Bind managed identities to dedicated Kubernetes service accounts; never use default service accounts | Entra ID / Kubernetes | Security | AIO Governance; Key Vault; Event Grid; Event Hubs; PostgreSQL; MySQL | AIO Governance; Key Vault; Event Grid; Event Hubs; PostgreSQL; MySQL
KV-001 | Phase 4 | Secrets / Key Vault | Create dedicated Key Vault boundary for POC / non-prod and separate from prod | Azure Key Vault | Security | Key Vault | Key Vault
KV-002 | Phase 4 | Secrets / Key Vault | Enable Azure RBAC permission model on Key Vault | Azure Key Vault | Security | Key Vault | Key Vault
KV-003 | Phase 4 | Secrets / Key Vault | Enable soft delete, purge protection, diagnostics, and expiration governance | Azure Key Vault | Security | Key Vault | Key Vault
KV-004 | Phase 4 | Secrets / Key Vault | Choose one secret delivery pattern: CSI provider for connected sites or Secret Store Extension for semi-disconnected sites | Azure Key Vault / Arc | Platform | Key Vault; PostgreSQL; MySQL; AIO Governance | Key Vault; PostgreSQL; MySQL; AIO Governance
KV-005 | Phase 4 | Secrets / Key Vault | Do not run the CSI provider and Secret Store Extension side-by-side in the same cluster | Azure Key Vault / Arc | Platform | Key Vault; PostgreSQL; MySQL; AIO Governance | Key Vault; PostgreSQL; MySQL; AIO Governance
KV-006 | Phase 4 | Secrets / Key Vault | Publish Key Vault through Private Endpoint and private DNS; disable public network access by default | Azure Key Vault / Networking | Security | Key Vault | Key Vault
GIT-001 | Phase 5 | GitOps / Policy | Enable Flux v2 GitOps and make Git the source of truth for baseline config | Azure Arc / Flux | Platform | AIO Governance; Event Grid; Event Hubs | AIO Governance; Event Grid; Event Hubs
GIT-002 | Phase 5 | GitOps / Policy | Create repo structure for platform, aio, site overlays, and optional db/eventing/storage/monitoring layers | Source Control / GitOps | Platform | AIO Governance | AIO Governance
POL-001 | Phase 5 | GitOps / Policy | Install Azure Policy for Kubernetes and start baseline controls in Audit mode | Azure Policy | Security | AIO Governance; PostgreSQL; MySQL | AIO Governance; PostgreSQL; MySQL
POL-002 | Phase 5 | GitOps / Policy | Define policy initiatives for cluster baseline, workload hardening, extension deployment, monitoring/Defender, labels/tags, network policies, and secret/cert standards | Azure Policy | Security | AIO Governance; Key Vault; Azure Monitor | AIO Governance; Key Vault; Azure Monitor
DEF-001 | Phase 5 | Threat Protection | Enable Defender for Containers on the Arc-connected cluster | Defender for Cloud | Security | AIO Governance; Event Hubs; Event Grid; ADLS | AIO Governance; Event Hubs; Event Grid; ADLS
NET-001 | Phase 6 | Network Segmentation | Implement default-deny Kubernetes NetworkPolicy in workload namespaces | Kubernetes Networking | Platform | AIO Governance; Event Grid; PostgreSQL; MySQL | AIO Governance; Event Grid; PostgreSQL; MySQL
NET-002 | Phase 6 | Network Segmentation | Allow only explicit east-west flows between AIO, approved apps, observability, and optional DB namespaces | Kubernetes Networking | Platform | AIO Governance; PostgreSQL; MySQL; Event Grid | AIO Governance; PostgreSQL; MySQL; Event Grid
NET-003 | Phase 6 | Network Segmentation | Keep database services ClusterIP only; do not expose via NodePort / public ingress | Kubernetes Networking | Platform | PostgreSQL; MySQL | PostgreSQL; MySQL
NET-004 | Phase 6 | Network Segmentation | Define site egress model (Arc gateway, explicit proxy, allowlist, private WAN) and approve Azure dependencies | Factory Network / Firewall | OT | AIO Governance; Azure Monitor; Event Hubs; Event Grid; ADLS | AIO Governance; Azure Monitor; Event Hubs; Event Grid; ADLS
MON-001 | Phase 7 | Observability | Pre-create and govern Azure Monitor workspace, Log Analytics workspace, Managed Grafana, and alert resources | Azure Monitor | Platform | Azure Monitor | Azure Monitor
MON-002 | Phase 7 | Observability | Enable Azure Monitor metrics and container insights for Arc-enabled K3s | Azure Monitor / Arc | Platform | Azure Monitor; AIO Governance | Azure Monitor; AIO Governance
MON-003 | Phase 7 | Observability | Define alerts for node health, restarts, AIO broker/connector failures, cert expiry, secret sync failures, private connectivity failures, and telemetry pipeline failures | Azure Monitor | Platform | Azure Monitor; Event Grid; Event Hubs; Key Vault; AIO Governance | Azure Monitor; Event Grid; Event Hubs; Key Vault; AIO Governance
MON-004 | Phase 7 | Observability | Use AMPLS + private connectivity for Azure Monitor where required | Azure Monitor / Networking | Platform | Azure Monitor | Azure Monitor
AIO-001 | Phase 8 | AIO Deployment | Deploy AIO with secure settings on the Arc-enabled K3s cluster | Azure IoT Operations | Platform | AIO Governance; Event Hubs | AIO Governance; Event Hubs
AIO-002 | Phase 8 | AIO Deployment | Use separate managed identities for AIO component access and secret synchronization | Azure IoT Operations / Entra ID | Security | AIO Governance; PostgreSQL; MySQL | AIO Governance; PostgreSQL; MySQL
AIO-003 | Phase 8 | AIO Deployment | Validate line-critical paths remain local-first and do not depend on cloud round trips | Azure IoT Operations | OT | AIO Governance; Event Hubs; Event Grid; ADLS | AIO Governance; Event Hubs; Event Grid; ADLS
MSG-001 | Phase 9 | Messaging | For Event Hubs path, deploy Standard or Premium namespace, not Basic | Azure Event Hubs | App | Event Hubs | Event Hubs
MSG-002 | Phase 9 | Messaging | Use Entra ID / managed identity for publishers and consumers; reserve SAS for exceptions only | Azure Event Hubs | Security | Event Hubs | Event Hubs
MSG-003 | Phase 9 | Messaging | Configure Event Hubs private endpoints or IP firewall rules and diagnostics | Azure Event Hubs | Security | Event Hubs | Event Hubs
MSG-004 | Phase 9 | Messaging | Define Event Hubs partitioning, throughput sizing, capture/archive, and DR approach if needed | Azure Event Hubs | App | Event Hubs | Event Hubs
MSG-005 | Phase 9 | Messaging | For Event Grid path, use cloud Event Grid as enterprise fan-out tier; keep line-critical events local | Azure Event Grid | App | Event Grid | Event Grid
MSG-006 | Phase 9 | Messaging | Define topic taxonomy, filters, and managed-identity-based downstream delivery where supported | Azure Event Grid | App | Event Grid | Event Grid
STO-001 | Phase 10 | Storage | Create ADLS Gen2 account with HNS enabled and managed-identity-first access | ADLS Gen2 | App | ADLS | ADLS
STO-002 | Phase 10 | Storage | Create raw, curated, and audit/evidence storage zones with RBAC + ACL path segmentation | ADLS Gen2 | App | ADLS | ADLS
STO-003 | Phase 10 | Storage | Create both Blob and DFS private endpoints with private DNS | ADLS Gen2 / Networking | Platform | ADLS | ADLS
STO-004 | Phase 10 | Storage | Enable container soft delete, blob soft delete, lifecycle policies, and immutability where required | ADLS Gen2 | Security | ADLS | ADLS
ANA-001 | Phase 11 | Analytics | If analytics is in scope, deploy Databricks Premium with Unity Catalog enabled from day one | Azure Databricks | App | Databricks | Databricks
ANA-002 | Phase 11 | Analytics | Use Access Connector / managed identity for storage credentials and service credentials | Azure Databricks / Entra ID | Security | Databricks | Databricks
ANA-003 | Phase 11 | Analytics | Apply compute policies, private connectivity, and audit log delivery before broad workspace use | Azure Databricks | Security | Databricks | Databricks
DB-001 | Phase 12 | Database | PostgreSQL path: deploy dedicated db-postgres and db-postgres-backup namespaces with ClusterIP-only exposure | PostgreSQL | App | PostgreSQL | PostgreSQL
DB-002 | Phase 12 | Database | PostgreSQL path: require TLS, hostssl-style access controls, SCRAM-SHA-256, role separation, and backup/WAL validation | PostgreSQL | App | PostgreSQL | PostgreSQL
DB-003 | Phase 12 | Database | MySQL path: deploy db-mysql plus optional router and backup namespaces with ClusterIP-only exposure | MySQL | App | MySQL | MySQL
DB-004 | Phase 12 | Database | MySQL path: require secure transport, host-scoped accounts, role separation, password controls, and backup/binlog validation | MySQL | App | MySQL | MySQL
RES-001 | Phase 13 | Recovery / Validation | Test cluster rebuild from code + Arc registration + extension deployment | Arc / GitOps | Platform | AIO Governance; Azure Monitor | AIO Governance; Azure Monitor
RES-002 | Phase 13 | Recovery / Validation | Test Key Vault object recovery and certificate rotation with dependent workload restart/reload | Key Vault / PKI | Security | Key Vault; Certificate Management; PostgreSQL; MySQL | Key Vault; Certificate Management; PostgreSQL; MySQL
RES-003 | Phase 13 | Recovery / Validation | Test ADLS delete recovery and database restore/cutover runbooks | ADLS / Database | App | ADLS; PostgreSQL; MySQL | ADLS; PostgreSQL; MySQL
RES-004 | Phase 13 | Recovery / Validation | Simulate WAN outage and validate local-first behavior, buffering/replay, restart behavior, and alerting | AIO / Messaging / Storage | OT | Key Vault; Event Hubs; Event Grid; ADLS; Azure Monitor | Key Vault; Event Hubs; Event Grid; ADLS; Azure Monitor
OPS-001 | Phase 14 | Operations | Publish runbooks for cluster onboarding, AIO deployment, secret sync failures, certificate rotation, eventing changes, storage recovery, monitoring failures, and DB restore/failover | Operational Runbooks | Platform | AIO Governance; Key Vault; Azure Monitor; Event Hubs; Event Grid; ADLS; PostgreSQL; MySQL | AIO Governance; Key Vault; Azure Monitor; Event Hubs; Event Grid; ADLS; PostgreSQL; MySQL
OPS-002 | Phase 14 | Operations | Define periodic access reviews and exception management for SAS, public access, broad Kubernetes privileges, and preview features | Governance / Operations | Security | Key Vault; Azure Monitor; Event Hubs; Event Grid; Databricks | Key Vault; Azure Monitor; Event Hubs; Event Grid; Databricks
OPS-003 | Phase 14 | Operations | Use ring-based change control for cluster, AIO, policy, monitoring, messaging, and database changes | Change Management | Platform | AIO Governance; Azure Monitor; Event Hubs; Event Grid | AIO Governance; Azure Monitor; Event Hubs; Event Grid

## RACI
Workstream / Deliverable | Platform Team | OT Team | Security Team | App Team
Define POC scope and site boundary | A | C | C | C
Approve landing zone, RG, tags, and ownership model | A | C | C | I
Build and harden K3s / Arc cluster | R | C | C | I
Enable OIDC, workload identity, custom locations, cluster connect | R | I | A | I
Design Key Vault boundary and private connectivity | R | I | A | I
Approve PKI / certificate issuer strategy | C | I | A | I
Implement secret delivery pattern (CSI or SSE) | R | I | A | C
Enable GitOps / Flux and baseline repos | A | I | C | R
Deploy Azure Policy and baseline initiatives | R | I | A | I
Enable Defender for Containers | R | I | A | I
Define in-cluster network policies | R | C | A | C
Approve site firewall / egress rules | C | A | C | I
Pre-create Azure Monitor / Log Analytics / Grafana | A | I | C | I
Define alert rules and runbooks | R | C | A | C
Deploy AIO secure settings | A | C | C | R
Design Event Hubs / Event Grid integration | C | C | C | A
Design ADLS layout, ACL model, and retention | C | I | C | A
Deploy Databricks and Unity Catalog (if in scope) | C | I | C | A
Deploy PostgreSQL or MySQL edge database | C | I | C | A
Test recovery / failover / disconnected operation | R | A | C | C
Publish operational handoff artifacts | A | C | C | C

## Backlog
Work Item | Phase | Feature | User Story | Acceptance Criteria | Primary Team
Epic 1 | Phase 0-1 | POC foundation | As the platform team, we need a defined site boundary, landing zone, tags, and ownership model so the POC can be governed consistently. | POC scope approved; RG/subscription created; tagging standard applied; owner map documented. | Platform
Epic 2 | Phase 2 | Arc-enabled K3s baseline | As the platform team, we need a hardened Arc-enabled K3s cluster with required Arc features so AIO can be deployed securely. | Cluster Arc-enabled; OIDC/workload identity/custom locations/cluster connect enabled; secrets encryption and audit logging enabled. | Platform
Epic 3 | Phase 3-4 | Identity, PKI, and Key Vault baseline | As the security team, we need workload identity, PKI decisions, and Key Vault secret delivery so workloads can authenticate without embedded credentials. | UAMIs created; service accounts mapped; Key Vault RBAC enabled; private endpoint and DNS validated; CSI or SSE pattern selected. | Security
Epic 4 | Phase 5 | Governance as code | As the platform and security teams, we need GitOps, Azure Policy, and Defender baselines so configuration drift is controlled and security posture is visible. | Flux configured; repos created; Policy extension installed in Audit mode; Defender for Containers enabled. | Platform/Security
Epic 5 | Phase 6-7 | Network and observability baseline | As the operations team, we need network segmentation and observability before go-live so failures can be detected and investigated. | Default-deny network policies in place; site egress approved; Monitor workspace, LAW, Grafana, and alerts deployed. | Platform/OT
Epic 6 | Phase 8 | AIO secure deployment | As the app/platform teams, we need AIO deployed with secure settings so local edge services are available using the approved control plane. | AIO deployed; secure settings enabled; local-first validation completed. | Platform/App
Epic 7 | Phase 9-10 | Cloud integration path | As the app team, we need eventing and storage services configured securely so curated edge data can flow to Azure. | Event Hubs/Event Grid selected and configured; ADLS private endpoints and ACL model validated; diagnostics enabled. | App
Epic 8 | Phase 11-12 | Optional analytics and database workloads | As the app team, we need optional Databricks and one edge database pattern deployed securely to support the POC scenario. | Databricks optional controls applied; PostgreSQL or MySQL deployed with TLS, namespace isolation, and backup validation. | App
Epic 9 | Phase 13-14 | Recovery and operational readiness | As all teams, we need recovery tests and runbooks completed so the POC can be operated and demonstrated with confidence. | WAN outage simulation completed; restore tests completed; handoff runbooks published; access reviews scheduled. | Platform/OT/Security/App